## Sheet1
Asset Register | [9 empty] | Risk Assessment | [5 empty] | Risk Treatment | [6 empty] | Residual Risk
No | Type | Asset | Location | Asset Owner | Asset Value |  |  |  |  | Threats | Vulnerability | Risk Description | Likelihood (Rating, Vector) | Impact (CIA) | Risk Level | Treatment Option | Selection of controls | Required Resources | Responsibility | Start Date | End Date | Remark | Probability(1,2,3) | Impact |  | Risk Level | Risk Treatment Options
[5 empty] | C | I | A | Cost | Value | [14 empty] | CIA | Score
1 | Information | Customer data | Data centers,Cloud storage | IT Department | 3 | 3 | 2 | 3 | 3 | Data breach involving customer data | Insufficient data encryption and protection | Exposure of customer personal | 4, Phishing attacks | (3,3,2) | High | Reduction | Encrypt data, implement strong access controls | 30 | IT Department | 2024-07-01 | 2024-07-25 | Periodic review needed | 2 | (2,2,2) | 2 | Medium | Data encryption, Strong access controls
2 | Hardware | Servers and network devices | Server rooms, Offices | Network Admin | 2 | 2 | 3 | 3 | 3 | DDoS attack on network infrastructure | Insufficient DDoS protection | Network services become unavailable, disrupting operations | 4, DDos | (2,2,3) | High | Reduction | Deploy DDoS protection services, monitor network traffic | 20 | Network Admin | 2024-06-15 | 2024-06-30 | Regular monitoring required | 2 | (2,2,2) | 2 | Medium | DDoS protection, Network monitoring
3 | Sofware | GPS tracking software | Map, Data centers | IT Department | 2 | 3 | 3 | 2 | 3 | GPS tracking software exploitation | Software vulnerabilities, lack of regular updates | Hackers manipulate GPS data, causing tracking inaccuracies | 3, Internet exposure | (2,3,3) | Medium | Reduction | Ensure regular software updates, conduct security assessments | 10 | IT Department | 2024-07-01 | 2024-07-20 | Continuous monitoring | 2 | (2,2,2) | 2 | Low | Regular updates, Security assessments
4 | Software | Fleet management software | Offices, Cloud storage | IT Department | 3 | 3 | 2 | 2 | 3 | Unauthorized access to sofware of company | Weak passwords and lack of multi-factor authentication | Unauthorized users alter fleet schedules and assignments | 2, Brute Force | (3,3,2) | High | Reduction | Implement strong passwords, enforce multi-factor authentication | 15 | IT Department | 2024-06-01 | 2024-06-18 | User training needed | 2 | (2,2,2) | 2 | Medium | Strong passwords, Multi-factor authentication
5 | Hardware | Web servers | Data centers, Cloud hosting | IT Department | 3 | 3 | 3 | 3 | 3 | Security breach of web servers | Vulnerability in web server software | Unauthorized access to web servers, compromising hosted services and data | 3, SQL Injection | (3,3,3) | High | Reduction | Regular software updates, vulnerability patching | 10 | IT Department | 2024-06-02 | 2024-06-19 | Regular monitoring required | 2 | (2,2,2) | 2 | Medium | Reduction, Patching
6 | Hardware | VPN gateways | Data centers, Offices | IT Department | 3 | 3 | 3 | 3 | 3 | VPN gateway compromise | Weaknesses in VPN configuration and management | Unauthorized access to the internal network through compromised VPN gateways | 2, BACKDOOR | (3,3,3) | High | Reduction | Implement strong encryption, enhance access controls | 10 | IT Department | 2024-06-03 | 2024-06-20 | Continuous monitoring | 2 | (2,2,2) | 2 | Medium | Reduction, Strong Encryption
7 | Hardware | Employee laptops | Offices, Remote work locations | IT Department | 2 | 3 | 2 | 2 | 3 | Theft or loss of laptops | Lack of encryption and tracking on devices | Loss of sensitive company data | 3, Physical theft | (2,3,2) | Medium | Reduction | Implement device encryption and tracking solutions | 10 | IT Department | 2024-07-01 | 2024-09-01 | Periodic reviews needed | 2 | (2,2,2) | 2 | Low | Device encryption, Tracking
8 | Information | Financial records | Data centers, Cloud storage | Finance Dept | 3 | 3 | 3 | 3 | 3 | Financial fraud | Inadequate access controls | Unauthorized access to financial records | 2, Fraud | (3,3,3) | High | Reduction | Enhance access controls, conduct regular audits | 10 | Finance Dept | 2024-08-01 | 2024-11-30 | Continuous monitoring | 2 | (2,2,2) | 2 | Medium | Access controls, Regular audits
9 | Hardware | Office workstations | Offices | IT Department | 2 | 3 | 2 | 2 | 3 | Malware infection | Lack of antivirus protection | Infection of workstations with malicious software | 3, Malware | (2,3,2) | Medium | Reduction | Install antivirus software, conduct regular scans | 20 | IT Department | 2024-09-01 | 2024-12-01 | Regular updates needed | 2 | (2,2,2) | 2 | Low | Antivirus software, Regular scans
10 | Software | Email servers | Data centers, Cloud hosting | IT Department | 3 | 3 | 2 | 2 | 3 | Email phishing attacks | Insufficient email filtering | Phishing attacks targeting employees | 4, Phishing | (3,3,2) | High | Reduction | Implement advanced email filtering, conduct phishing awareness training | 20 | IT Department | 2024-07-01 | 2024-10-01 | Regular updates needed | 2 | (2,2,2) | 2 | Medium | Email filtering, Awareness training
11 | Software | Ticketing System | Internal System | IT Department | 3 | 2 | 3 | 3 | 3 | Attack on ticketing system | No DDoS protection for ticketing system | Ticketing system becomes non-functional during attack | 3, Malware | (2,3,3) | High | Reduction | Encrypt data and enhance access controls | 30 | IT Department | 2024-06-01 | 2024-09-01 | Regular updates needed | 2 | (2,2,2) | 2 | Medium | Implement DDoS protection and regular monitoring for ticketing system
12 | System | Cloud Services | Cloud Platform | IT Department | 2 | 2 | 3 | 3 | 3 | Unauthorized access to cloud services | Weak access controls and poor monitoring | Data and services on cloud platform compromised | 3, Misconfiguration | (3,3,3) | High | Reduction | Encrypt data and Implement strict access controls | 25 | IT Department | 2024-06-02 | 2024-08-01 | Periodic reviews needed | 2 | (2,2,2) | 2 | Medium | Strong Encryption
13 | Digital assets | Social Media Accounts | Online | Marketing Dept | 2 | 3 | 2 | 2 | 3 | Hacking of social media accounts | Weak passwords and poor monitoring | Unauthorized access to social media accounts, brand damage | 3, Phishing | (2,3,2) | Medium | Reduction | Enforce strong passwords, implement MFA, monitor accounts | 15 | Marketing Dept | 2024-06-01 | 2024-07-01 | User training needed | 2 | (2,2,2) | 2 | Low | Regular updates, Security assessments
14 | System | IoT Sensors | Infrastructure Software | IT Department | 2 | 3 | 2 | 2 | 3 | Unauthorized access to IoT sensors | Lack of monitoring and access controls | Unauthorized access and control over IoT sensor data | 3, Network vulnerabilities | (2,3,2) | Medium | Reduction | Implement monitoring and strict access controls | 25 | IT Department | 2024-06-02 | 2024-08-02 | Continuous monitoring | 2 | (2,2,2) | 2 | Low | Strict access controls for IoT sensors
15 | Software | Payment Processing Systems | Data Center | IT Department | 3 | 3 | 3 | 3 | 3 | Unauthorized access to payment processing systems, Fraud | Weak access controls | Unauthorized access leading to fraud and data theft | 3, Phishing, malware | (3,3,2) | High | Reduction | Implement strong access controls, encryption, and monitoring | 30 | IT Department | 2024-06-03 | 2024-08-03 | Regular updates needed | 2 | (2,2,1) | 2 | Medium | Regular updates