## Trang_tính1
Risk ID | Control | Priority | Cost | Timeline/Strategy | Responsible Team
1 | Advanced encryption and data protection | High | 50000 | 6 months | IT Security Team
2 | Robust DDoS protection solutions | High | 40000 | 4 months | Network Admin Team
3 | Regular software updates and vulnerability scanning | Medium | 20000 | 3 months | IT Department
4 | Multi-factor authentication and strong password policies | High | 25000 | 2 months | IT Department
5 | Regular security audits and patch management | Medium | 30000 | 4 months | IT Security Team
6 | Enhanced VPN configuration and management | Medium | 15000 | 3 months | Network Admin Team
7 | Endpoint security software, encryption, regular updates | High | $40,000 | 3 months | IT Department
8 | Encryption, access controls, regular audits | High | $70,000 | 4 months | IT Department
9 | Endpoint security, regular updates, access control | Medium | $20,000 | 6 months | Finance Dept
10 | Spam filters, encryption, MFA | High | $50,000 | 3 months | IT Department
11 | Access controls, regular security assessments | Medium | $20,000 | 6 months | IT Department
12 | Strong encryption, access control, regular security assessments | High | $90,000 | 4 months | IT Department
13 | Strong passwords, MFA, regular monitoring | Medium | $10,000 | 3 months | Marketing Dept
14 | Secure network design, regular firmware updates | Medium | $35,000 | 6 months | IT Department
15 | PCI-DSS compliance, encryption, regular audits | High | $100,000 | 4 months | IT Department